## Tabelle1
Priority scale | high | medium | low | trivial |  | Storypoints: Fibonacci-Reihe bis 21
Business Value scale | 4 | 3 | 2 | 1 |  | 1,2,3,5,8,13,21
Priority | BusinessValue | Product Goal | Theme | US_ID | As a… | I want to be able to … | So that… | StoryPoint | Estimates (hours) | Acceptance Criteria
high | 4 | Product Goal 1 - Basic User Interface | Create habit | 1 | User | create a new habit. It should be possible to select it as a reoccuring habit or a one time action. | I can create a new habit. | 2 | 5 | - The user can create a habit - The habit is automatically saved to a database - There is a button to select the reoccurance of the habit
high | 4 | Product Goal 1 - Basic User Interface | Main menu | 2 | User | open the application in the main overview window. It should have enough space to fit the most important information | I automatically get redirected to the main overview and don't have to find it through different menus. | 13 | 31 | - When opening the web application the user is in the main window - The main window contains space holders for: - Habit creation - The level bar - Current open habits - A switch to toggle between showing all habits and the currently open ones.
high | 4 | Product Goal 1 - Basic User Interface | Display information | 3 | User | display the most important information, like current habits in the main window. | I instantly get the most information without having to look for them. | 3 | 8 | - All relevant data is loaded from the database - All relevant data is displayed in the placeholders - The relevant data could be the following - Habits - The current level
medium | 4 | Product Goal 2 - Basic Gamification Features | Gain Experience | 4 | User | gain experience when finishing a habit. | I get the reward for finishing a habit. | 3 | 8 | - When completing a habit, the user should be rewarded with Experience points - These should be displayed directly when the task is marked as completed.
medium | 3 | Product Goal 3 - Advanced Features | Dynamic experience gain | 5 | User | gain dynamic amounts of experience - not always the same for the same habit. | I constantly get challenged to better myself. | 13 | 30 | - Experience gain should be adjusted over time - If a person completes the same habit multiple times in a row, the experience gain should decrease - If he ups his goals, he should be rewarded with increased experience gain
high | 4 | Product Goal 2 - Basic Gamification Features | Level up | 6 | User | level up based on the experience I've gained. | I get rewarded for staying consistent. | 2 | 5 | - If the user has accumulated enough experience points, he should level up.
medium | 3 | Product Goal 3 - Advanced Features | Streak bonus | 7 | User | gain more experience when on a streak, completing habits in a constant manner. | I get rewarded for staying consistent. | 5 | 12 | - The user is able to gain bonus experience if he completes the same habit multiple times in a row, without missing a scheduled habit.
high | 4 | Product Goal 1 - Basic User Interface | Edit and delete habits | 8 | User | edit and delete habits that I've already created previously. | I have full c ontrol over the habits I currently want to create. | 3 | 8 | - The user can edit a habit that has already been created - This can be done through a button in the ui.
medium | 3 | Product Goal 2 - Basic Gamification Features | Get rewards | 9 | User | gain rewards by leveling up and finishing habits. | I get rewarded for staying consistent. | 8 | 20 | - The user gets occasional rewards by leveling up - These rewards can be displayed in another menu
high | 3 | Product Goal 4 - User Documentation | User documentation | 10 | User | understand the workings of the application and have some form of documentation. | in case I get questions about the application, I can always look them up. | 13 | 30 | - The documentation contains all files required for the evaluation